## Slide 1: Procurement of Construction
Water Sector Program

## Slide 2: Micro Purchase
Procurement by micro‐purchase is the acquisition of services, the aggregate dollar amount of which does not exceed the micro‐purchase threshold of $10,000.00.
To the extent practicable, the non‐federal entity must distribute micro‐purchases equitably among qualified suppliers.
Micro‐purchases may be awarded without soliciting competitive quotations if the non-federal entity considers the price to be reasonable.

## Slide 3: Small Purchase
This is a simple and informal method used for securing services, supplies, or other property that do not cost more than the Small Purchase procedures provided by the Louisiana Procurement Code R.S. 39:1596, are currently $30,000.
Small purchase procurement consists primarily of a comparison of quotations to each other and to other sources of pricing information (e.g., past prices paid, catalog prices, etc.).
This procurement method should be used when an item or a service can be solicited through a simple description, so that all potential vendors can understand and offer a quote.

## Slide 4: Small Purchase
Another procurement method should be used if a scope of work consists of several tasks, detailed specifications, or selection procedures, such as formal evaluations, determining competitive ranges, conducting detailed negotiations, or requesting best and final offers are required.
Any procurement exceeding the State Small Purchase procedures must be conducted using another procurement method.
The Grantee shall not break down requirements aggregating more than the small purchase threshold to avoid any requirements that apply to purchase that exceed the State Small Purchase procedure

## Slide 5: Sealed Bids
Method used to purchase materials or supplies costing more than $30,000 (or if the Grantee chooses not to follow the small purchase procedure) and for construction services. Used when the primary basis for award is cost.
Should have two or more responsible bidders willing and able to compete effectively for the business.
Initiated by publishing an advertisement for bids. Also bids must be solicited from an adequate number of known suppliers, providing them sufficient response time prior to the date set for opening the bids.

## Slide 6: Sealed Bids
Must hold a public bid opening at the time and place set in the advertisement for bids.
Must have a written review and tabulation of bids according to selection criteria.
Contract must be awarded to the lowest responsive and responsible bidder.
Must be a firm fixed‐price contract (fixed price or unit price).
Any or all bids may be rejected if there is a sound documented reason.
A contract detailing a scope of work and the terms of compensation is executed.

## Slide 7: Contracts and Prices
Sealed Bid method is the preferred method for procuring construction services with a firm fixed-price contract (lump sum or unit price) is awarded
Firm fixed‐price. This contract type requires the delivery of products or services at a specified price, fixed at the time of contract award and not subject to any adjustment on the basis of the contractor’s cost experience in performing the contract.
  Its advantages are that it encourages contractor efficiency and places total responsibility and risk on the contractor.
  Its disadvantages are that it lacks flexibility in pricing and performance.
  It is the most preferred type of contract and the most commonly used, requiring the least amount of contract administration.

## Slide 8: Contract Prices
Lump Sum Price
For definable work product(s) or deliverable(s) whose value can be expressed as a single price inclusive of all production costs [labor, materials and purchased service costs, allowable overhead and profit]. The contractor will bear all the risks in producing the work product or deliverable at the agreed upon price.
Because of the presumed certainty of contract task or item performance that qualifies a contract task or item as a Lump Sum price no adjustments to contract price are permitted.
Payment of total contract price will be made upon satisfactory performance, delivery and final acceptance of contract task(s) or item(s).

## Slide 9: Contract Prices
Unit Price
For definable work products or deliverables whose value can be expressed as a single price inclusive of all production costs [labor, materials and purchased service costs, allowable overhead and profit] for contract tasks or items and will be needed in two more iterations at the same agreed upon price.
The contractor agrees to bear all the risks and cost variance in producing or performing the contract tasks or items at the agreed upon price per unit and for the quantities specified.
For fixed price contracts, no change in quantities are permitted.

## Slide 10: Selecting the Right Procurement Method, Contract Type and Price
Typically for a small purchase a single payment be made upon completion delivery/performance.
Finally, to qualify as a small purchase the total acquisition cost cannot exceed $30,000.
If the purchase requires specifications or a detailed scope of work and cannot be simply described, then the sealed bid method is appropriate.
If public advertisement of specifications is required, the sealed bid method must be used.
The sealed bid method is required for construction services and can also be used for equipment, materials and some non‐professional services.

## Slide 11: Materials, Supplies, and Construction Services
The procurement process must be in accordance with the federal requirements of 2 CFR 200.318‐326 and Louisiana’s Public Bid Law.
One of the three methods below must be followed when procuring materials and supplies and construction services.
  Micro-Purchase
  Small Purchase
  Sealed Bid

## Slide 12: Bid Package Documents, Advertising for Bids, and Bid Opening Procedures
A bid package includes technical bid specifications — usually by an architect or engineer on the basis of prepared plans or working drawings.
These specifications must provide a clear and accurate description of technical requirements for materials and products and/or services to be provided on the project.
Additionally, the plans and specifications must be stamped by an architect or engineer registered in Louisiana.

## Slide 13: Bid Package Documents, Advertising for Bids, and Bid Opening Procedures
If the project falls under the jurisdiction of another state agency (e.g., Department of Health and Hospitals for sewer and water projects), the plans and specifications must also be approved by the cognizant state agency prior to construction.
It is recommended that the approval be received prior to the advertisement for bids.
Documentation of that approval must be included in the Grantee’s files.

## Slide 14: Bid Package Documents, Advertising for Bids, and Bid Opening Procedures
All public works contracts must contain a clause stating that any punch list generated during a construction project shall include the cost estimates for the particular items of work the design professional has developed.
The estimates will be based on the mobilization, labor, material, and equipment costs of correcting each punch list item.
The design professional must retain in his/her working papers documentation used to determine the cost of the punch list items should these matters be disputed at a later date.
The Grantee must not withhold from payment an amount more than the value of the punch list.

## Slide 15: Bid Package Documents, Advertising for Bids, and Bid Opening Procedures
Punch list items completed by the contractor/subcontractor(s) must be paid for upon the expiration of the forty‐five-day lien period.
The base bid must include all components of the approved project.

## Slide 16: Public Bid Law
  The advertisement for any contract for public works must be published once a week for three different weeks in a newspaper in the locality, and the first advertisement must appear at least 25 days before the opening of bids for construction projects.
  For materials purchases, the advertisement must be published two times in a newspaper in the locality, and the first advertisement must appear at least 15 days before the opening of bids.
  The first series of advertisement(s) cannot occur on a Saturday, Sunday, or legal holiday.
  Plans and specifications must be available to bidders on the day of the first advertisement and must be available until 24 hours before the bid opening date.
  The advertisement must call the bidders’ attention to the conditions of employment and requirements of federal prevailing wage rates, Segregated Facilities, Section 3, and Equal Opportunity.

## Slide 17: Public Bid Law
  The advertisements cannot be published on Saturdays, Sundays, or a legal holiday.
  Parishes with a population exceeding 20,000 and city or municipality with a population exceeding 10,000 in population shall provide a uniform and secure electronic interactive system for the submittal of bids.
The Public Bid Law states that if bid documents are amended during the advertisement period, addenda must be sent to all prospective bidders who have received bid documents. Additionally, it states that no public entity shall issue or cause to be issued any addenda modifying plans and specifications within a period of 72 hours prior to the advertised time for the opening of bids, excluding Saturdays, Sundays, and any other legal holidays.

## Slide 18: Public Bid Law
If the necessity arises to issue an addendum modifying plans and specifications within the 72‐hour period prior to the advertised time for the opening of bids, then the opening of bids must be extended for at least 7 days, but not to exceed 21 days, without the requirement of re‐advertising the project. The addendum must state the revised time and date for the opening of bids.
A copy of each addendum must be submitted to the Office of Community Development at the time the addendum is issued, including addenda solely pertaining to federal wage rate decisions.

## Slide 19: Public Bid Law
All bids received prior to the opening of bids must remain sealed and kept in a safe place until the bid opening.
On the date scheduled, the public bid opening should be conducted.
The bids must be read aloud during bid opening, and the apparent low bidder should be determined during the bid opening.
However, the bids must also be reviewed for both technical and legal responsiveness of bids.
In addition, the bidders must be evaluated as having the capacity to furnish products and/or services required.

## Slide 20: Public Bid Law
Pursuant to LRS 38:2227, public entities are required to obtain an attestation regarding past criminal convictions, if any, from each bidding entity responding to advertisements and letting for bids for public works contracts.
Also, pursuant to LRS 38:2212.10, all bidders and contractors performing physical services with public entities must be registered and participate in a status verification system to verify that all employees in the state are legal citizens of the United States, or are legal aliens.

## Slide 21: Awarding a Contract
Contracts must be awarded to the “lowest responsible bidder” in accordance with the Louisiana Public Bid Law.
Discretion has been given to public entities to determine bidder responsibility. A Court decision has concluded that, in determining bidder responsibility, the public entity may look to financial ability, skill, integrity, business judgment, experience, reputation, quality of previous work on contracts, and other similar factors bearing on the bidder’s ability to successfully perform the contract.
If the Grantee proposes to disqualify a bidder on the grounds that the bidder is not a “responsible bidder”, it must (1) give written notice of the proposed disqualification to the bidder and include in the notice all reasons for the proposed disqualification, and (2) give the bidder the opportunity to be heard at an informal hearing at which the bidder is afforded the opportunity to refute the reasons for the disqualification.

## Slide 22: Issuing a Notice to Proceed
After execution of the contract documents and notification to the contractor(s) and subcontractor(s) of their responsibilities, a Notice to Proceed must be issued to each prime contractor.
The notice should state the construction start date and the scheduled completion date.
Do not submit a copy of the Notice to Proceed to this office.
The contract file and associated compliance files should be reviewed by the Grantee to ensure all documentation is complete.

## Slide 23: Issuing a Notice to Proceed
The following is a list of construction contract file requirements:
  Preliminary design and cost estimates
  Final design documents and cost estimates
  Evidence that all necessary land or easement acquisition has been completed prior to advertising for bids;
  Bid documents; Documentation of submittal to and approval of plans and specifications by the cognizant state/federal agency having jurisdiction over the project
  Certification of Compliance with Architectural Barriers Act, if applicable
  Proof of publication/copy of advertisement for bids
  Minutes of public bid opening
  Tabulation of bids

## Slide 24: Issuing a Notice to Proceed
The following is a list of construction contract file requirements continued:
  Recommendation for award
  Notice of contract award
  Executed contract document;
  Certification of insurance/bonding
  Notice to Proceed
  Documentation verifying prime contractor and all subcontractors have an active UEI number
  Evidence of project sign

## Slide 25: Construction Management
The Grantee is responsible for monitoring the construction of the Water Sector project to ensure that the contractor is operating in compliance with technical specifications and state and federal requirements, maintaining adequate cost and budget controls, and processing necessary contract changes in order to bring the contract to completion.
Upon receiving the Notice to Proceed, the contractor must submit a cost breakdown showing the amount assigned to each portion of the work.
This breakdown must be reviewed by the Grantee and its architect/engineer and used as the basis for requests for payment discussed.
The breakdown should be submitted to the Grantee within 5‐10 days of receipt of the Notice to Proceed.

## Slide 26: Construction Management
Construction management must include inspection and general supervision of construction to check the contractor's work for compliance with the drawings and specifications and quantity/quality control.
Written inspection reports must accompany the contractor's requests for partial payment to the Grantee

## Slide 27: Inspecting & Accepting the Work, Closing Out the Project, and Making the Final Payment
In accordance with LRS 38:2248, a maximum of ten percent retainage on construction contracts which are less than $500,000 and a maximum of five percent retainage on construction contracts which are $500,000 or more can be retained by the Grantee.
When construction work has been completed, the contractor must certify completion of work and submit a final request for payment.
The architect/engineer must make the final inspection and prepare a written report of the inspection prior to issuance of final payment, less retainage.

## Slide 28: Procurement Staff
Kristie Galy, Program Manager
  Kristie.galy2@la.gov
  225-342-2800
Denease McGee, Financial Analyst
  Denease.mcgee2@la.gov
  225-342-7530
William Hall, Grant Specialist
  William.hall@la.gov
  225-219-3613