## Components
| Procurement Components |  |  |  | Main Page |  |  | Click on hyperlinks for definitions | [8 empty] | 24. 9. 25
| Categories of Purchases |  |  | Methods of Procurement |  |  | Contractor Selection |  |  | Solicitation Types |  | Contract Types |  | Prices |  | Payment Types
1 | Design Specifications Purchase. |  | 1 | Micro-Purchase |  | 1 | Price |  | 1 | Quote | 1 | Firm fixed‐price | 1 | Lump Sum Price | 1 | Single Completion Payment
2 | Specified Product, Brand Name or Equal Specifications Purchase. |  | 2 | Simplified Acquisition |  | 2 | Qualifications |  | 2 | Invitation for Bids | 2 | Cost‐reimbursement | 2 | Unit Price | 2 | Partial Completion Payment
3 | Functional or Performance Specifications Purchase. |  | 3 | Sealed [Advertised] Bid |  | 3 | Combination |  | 3 | Request fo Proposal | 3 | Time and Materials contract | 3 | Billable Hours | 3 | Progress Payment
4 | Scope of Work (SOW) Purchase |  | 4 | Competitive Proposals | [8 empty] | 4 | Reimbursable Costs
The sealed bid approach to competitive procurements is typically only used for construction projects, purchases of equipment widely available in the commercial marketplace, and procurement of supplies in bulk.
No uncertain performance
All vendors offer the same product
All cost components are known
when precise specifications can be developed and a firm fixed-priced contract will be awarded to the responsive bidder based principally on price
with payment terms to be negotiated with selected firms based on funding programs allowable engineering fees.
with payment on a billable hour pricing on a task completion basis.
intent of the Village is to award a cost reimbursement contract with payments on a billable hour pricing on a task completion basis.
intent of the Village is to award a cost reimbursement contract with pricing for billable hours basis on a task completion basis.
Simplified Acquisition
may not be used if any of the following are applicable
If the purchase categories are for Scope of Work or Performance Specifications
If the purchase is for products or services in which there are complex questions to be considered or specific contract provisions to be included (inspection and testing, insurance, patents, price adjustments, etc.);
If the purchase is for studies and services or has other features that may require technical evaluation, qualitative assessment, or involve negotiations, and where an award cannot be made confidently on the basis of the lowest price,
If the purchase is for consultant services that require a more defined work statement and multiple delivery schedules, different work products, deliverables and/or contingent or uncertain performance requirements including the quantities or iterations of the purchase are needed.

## Planning
Main Page
Instructions For each proposed item to be procured; describe the purchase, the estimated cost and fill out all the procurement components. When completed, print out and include in he application.
Procurement Planning
Applicant Community
Grant Program FY |  | Eligible Activity
Description of purchase or activity:
Approximate/Proposed Price
Units/iterations | Estimated Price per iteration/unit |  | Approximate total price
0 | 0 |  | 0
Procurement Components for this purchase
Component |  |  | For this purchase
Purchase Type: |  |  |  |  | Design Specifications Purchase. | Specified Product, Brand Name or Equal Specifications Purchase. | Functional or Performance Specifications Purchase. | Scope of Work (SOW) Purchase
Method of Procurement: |  |  |  |  | Micro-Purchase | Simplified Acquisition | Sealed [Advertised] Bid | Competitive Proposals
Contractor Selection: |  |  |  |  | Price | Qualifications | Combination
Solicitation Types: |  |  |  |  | Quote | Invitation for Bids | Request fo Proposal
Contract Type: |  |  |  |  | Firm fixed‐price | Cost‐reimbursement | Time and Materials contract
Types of Price: |  |  |  |  | Lump Sum Price | Unit Price | Billable Hours | Reimbursable Costs
Payment Type: |  |  |  |  | Single Completion Payment | Partial Completion Payment | Progress Payment
Click on links above to review definitions and click on"Planning" to return to this tab.
Demolition of homes, with asbestos removal, land clearing and disposal

## Purchases
|  | Main Page |  | Planning
Purchase Types |  |  |  |  | Below are the four different federal categories of purchase types. They are mutually exclusive.
Design Specifications Purchase. | [7 empty] | Main Page | Public Works
Design specifications contain a description of the item desired as opposed to performance standards. Design specifications may be as detailed as needed. Depending on the nature of the item, the design specifications may contain precise measurements, tolerances, materials, product tests, quality control, and other detailed information, provided competition is not being limited to one product.
[8 empty] | Main Page | Equipment, Supplies
Specified Product, Brand Name or Equal Specifications Purchase.
Under this form of specification, clear and accurate product descriptions are developed. These descriptions shall not contain features that unduly restrict competition. It may be necessary to describe technical requirements for materials and equipment by referencing brand name products in order to define performance or other salient requirements. References to brand names shall be followed by the words “or equal” and a description of the item’s essential characteristics so that competition is not restricted.
Main Page
Functional or Performance Specifications Purchase.
These specifications contain performance characteristics that are desired for the item or that identify how the item functions. The detailed design or exact measurements are not stated.
[8 empty] | Main Page | Contracted Services
Scope of Work (SOW) Purchase
A SOW provides a basis for mutual understanding between the [purchase/procurement authority] and the offeror and subsequent contractor of the [UGLG/NFE Subrecipient]’s requirements. A scope of work is developed at the beginning of the procurement cycle and is a written description of the entity’s needs and desired outcomes for the procurement and becomes the basis for any resulting solicitation. The scope of work helps to ensure that the product(s) or service(s) meets the stated outcome and establishes the parameters of the resulting contract.
Every SOW shall include:
1. Detailed work and task requirements including number of iterations or units;
2. End results and deliverables, including the criteria, which a deliverable must meet to be considered acceptable;
3. Delivery schedules/period of performance;
4. Any reporting and compliance requirements;
5. A precise statement of the objectives;
A SOW purchase is typically solicited through a |  |  |  |  | Request for proposals |  |  | because the contractor selection
will be made on a |  | Combination |  | [Price and Qualifications] |  | basis. However a SOW purchase can also be
made on a | Price | selection basis |  | with a | lump sum price |  | for different performance requirements instead of
billable hours |  | or | reimbursable costs. |  | The contract can either be a |  |  | fixed price | with specified quantities, or a
cost re-imbursement |  |  | type, with a cost ceiing and payments made on a |  |  |  | partial completion |  | basis.

## Methods
| Main Page | Planning | Below are the four different federal grant procurement methods of conducting procurement. They are mutually exclusive and their use are also governed by cost. thresholds
Methods of Procurement
Main Page
Micro-purchases for Contracts that Do Not Exceed $10,000 – This value is set by the Federal Acquisition Regulation (FAR) at 48 C.F.R. part 2, subpart 2.1 (Definitions) and is periodically adjusted for inflation. These purchases may be made without obtaining competitive quotes if the recipient determines the price to be paid is fair and reasonable. These purchases should be distributed equitably among qualified suppliers in the local area and purchases should not be split to avoid the requirements for competition above the $10,000 micro-purchase threshold.
Main Page
Simplified Acquisition Threshold or Small Purchases – Small purchase procedures may be used to acquire services, supplies, or other property valued at more than the micro-purchase threshold (currently set at $10,000) but less than the Federal Simplified Acquisition Threshold, set by the Federal Acquisition Regulation at 48 C.F.R. Subpart 2.1 in accordance with 41 U.S.C. § 403(11), currently set at $250,000. (Note: This threshold is periodically adjusted for inflation. For the latest threshold, refer to 48 C.F.R. Subpart 2.1.) For small purchases, recipients must obtain price or rate quotes from an adequate number of qualified sources.
Restrictions on use: Simplified Acquisition/Small purchase procedures may not be used when: Purchasing products or services in which there are complex questions to be considered or specific contract provisions to be included (inspection and testing, insurance, patents, price adjustments, etc.). Purchasing complex studies and services or other requirements which may require technical evaluation or involved negotiations, and where award cannot be made confidently on the basis of low price. In these cases, use more formal methods for soliciting sealed bids or requesting proposals. Purchasing consultant services which may require a more defined work statement and multiple delivery schedules or deliverables. Complex or detailed specifications are not appropriate for simplified acquisition/small purchase transactions and may discourage potential sources from providing a quote.
Main Page
Sealed Bid (Advertised) – Sealed bidding is a generally accepted procurement method in which bids are publicly solicited, and a firm fixed price contract (lump sum or unit price) is awarded to the responsible bidder, whose bid, conforming to all the material terms and conditions of the invitation for bids (IFB), is lowest in price. Sealed bidding does not allow the recipients to evaluate the merits of technical proposals and to pay more for a higher quality product. Rather, it requires the award be made to the bidder who meets the technical requirements in the solicitation, even if the product is only minimally acceptable. Therefore, the contract specifications should precisely describe the recipient’s minimum requirements that the contractor will be contractually bound to meet. Sealed bidding is appropriate when precise specifications can be developed and a firm fixed-priced contract will be awarded to the responsive bidder based principally on price. The sealed bid approach to competitive procurements is typically only used for construction projects, purchases of equipment widely available in the commercial marketplace, and procurement of supplies in bulk.
Main Page
Competitive Proposals (Request for Proposal) – Competitive proposals, commonly known as a request for proposals, or RFP, are a generally accepted procurement method when the nature of the procurement does not lend itself to sealed bidding and the recipient expects that more than one source will be willing and able to submit an offer or proposal. It is required in circumstances when the UGLG needs or wants to evaluate more than just price. Federal agencies do not require use of competitive negotiations/proposals for any particular procurement. This method is simply one of many that may be used, as appropriate and when permitted by State or local laws. Competitive negotiations/proposals offer an important advantage over sealed bids—they afford the recipient and the offerors an opportunity to discuss/negotiate important aspects of the project, including the impact that the offeror’s perceived performance and schedule risks have on the price being offered. These discussions may very well result in negotiated adjustments to the specifications, delivery schedule, etc. and thus a more cost effective approach to accomplishing the project objectives. In contrast to competitive negotiations/proposals, the sealed bid method affords no opportunity to discuss or negotiate the price, specifications, delivery requirements, or other important aspects of the contract, such as a contractor’s key personnel, insurance, warranties, etc Another important advantage of competitive negotiations is that it allows the recipient to choose the winning proposal on the basis of factors other than price alone. For example, the recipient may choose the proposal that represents the “best value” to the agency. Under this method, the recipient makes tradeoffs between price and technical factors in determining the best overall value to the agency. Whenever using the Competitive Proposal method there are additional requirements below.
When using the competitive proposal method the UGLG must select the qualitative evaluation factors in addition to price/cost that
will determine the contractor will yield the best value:
Evaluation Factors
After selecting the evaluation subjects the UGLG will then need to select the appropriate scoring method for evaluating the qualitative factors:
Scoring Methods
The federal grant procurement regulations require that UGLGs must have written procedures for conducting the evaluation of the non-price
evaluation factors. HUD further requires that UGLGs shall prepare an evaluation report to document the ranking of the proposals by technical merit, using point scores, or similar methodology. A methodology for conducting the evaluation can be found at:
Evaluation Plan
Procurement by Noncompetitive Proposal (Sole Source) – Procurement by noncompetitive proposals is procurement through solicitation of a proposal from only one source (a/k/a a “sole source”). Noncompetitive or sole source procurements may be used only when one or more of the following circumstances apply: (1) The item is available only from a single source; (2) The public exigency or emergency for the requirement will not permit a delay resulting from competitive solicitation; (3) The Federal awarding agency or pass-through entity expressly authorizes noncompetitive proposals in response to a written request from the non- Federal entity; or (4) After solicitation of a number of sources, competition is determined inadequate. 2 C.F.R. § 200.320(f). Federal agency acknowledges that sole sourcing is generally an accepted procurement method; however, it is one that is subject to close scrutiny due to the limited circumstances which justify its use. If the recipient decides to solicit an offer from only one source, the recipient must justify its decision adequately in light of the standards discussed in Section 2.8 (Other than Full and Open Competition). Recipients should retain copies of its sole source award justification in its procurement files. In some circumstances, Federal agency may request that the recipient provide Federal agency with a sole source justification before entering into the contract.

## Selection
| Main Page | Planning
Below are the three different methods that can be utilized for selecting a contracting.
Contractor Selection
|  |  | Main Page | SOW
Price -offers are solicited, and a firm fixed price contract (lump sum or unit price) is awarded to the responsible offeror, whose quote or bid, conforming to all the material terms and conditions of the request for qoutes or invitation for bids (IFB), is lowest in price. Selection by price does not allow the recipients to evaluate the merits of technical (or qualitative evauation factors) proposals and to pay more for a higher quality product. Rather, it requires the award be made to the offeror with the lowest price which meets the technical requirements in the solicitation, even if the product is only minimally acceptable. Price, which is considered the best value, is typically the only selection factor when using the Quote or Bid method of solicitation.
|  |  | Main Page | Evaluation
Qualifications-Based Procurements for Architectural and Engineering Services (A&E) – to acquire program management, architectural engineering, construction management, feasibility studies, preliminary engineering, design, architectural, engineering, surveying, mapping, or related services for a federal agency-funded project. The most appropriate professional or firm is selected based on qualification factors such as knowledge, skill, experience, and other project-specific factors, rather than on fees. The nature of the services to be performed and its relationship to construction, not the nature of the prospective contractor, determines whether qualifications-based procurement procedures may be used. Federal agency has long administered the requirement for using qualifications-based procurement procedures for selection of contractors that perform A&E services, generally associated with the construction, alteration, or repair of real property. Federal agency’s interpretation of 49 U.S.C. § 5325(b) is consistent with typical Federal policies implementing the “Brooks Act,” 40 U.S.C. § 1102, which limits qualifications-based procurement procedures to research, planning, development, design, construction, alteration, or repair of real property. Thus if services, such as program management, feasibility studies, or mapping, are not directly in support of, directly connected to, or directly related to, or lead to construction, alteration, or repair of real property, then the recipient may not use qualifications-based procurement procedures to select the contractor that will perform those services.
|  |  | Main Page | SOW
Combination (Best Value). Due to the nature of the procurement, contract award need not be based exclusively on price or price-related factors. The nature of the requirement is such that the UGLG needs to evaluate more than just price to be sure that the prospective contractor understands the UGLG’s needs and can successfully complete the contract, especially when contracting for professional services in different types of negotiated acquisitions, the relative importance of cost or price may vary. When the recipient’s material requirements are clearly definable and the risk of unsuccessful contract performance is minimal, cost or price may play a dominant role in source selection. The less definitive the requirements, the more development work required, or, the greater the performance risk, the more technical or past performance considerations play a dominant role in source selection. All of these considerations tend to supersede the need for the low-priced bid. Selection by Combination does allow the recipients to evaluate the merits of technical (or qualitative evauation factors) proposals and to pay more for a higher quality product when it is documented by the non-cost evaluation factors used to make the selection.

## Solictation
| Main Page |  | Planning
Below are the three different types of solicitation methods that can be utilized procurement. They are mutually exclusive and their use may be goverened by cost thresholds.
Solicitation Types.
Main Page
Quote - a solicitation of pricing information from several sources based upon a simple description of a defined work product or completed service. A Quote is normally expressed as a single price inclusive of all the necessary cost components furnished by the vendor. All vendors are expected to provide essentially the same product or service for the offered price. The lowest price/cost Quote will be the best value. The solicitation can establish acceptability standards or minimum qualifications for offers, but selection must be made on price. A Quote is not necessarily an offer and, consequently, does not have to be accepted by the [UGLG/ Subrecipient] to form a binding contract. Therefore, issuance by the [UGLG/ Subrecipient] of an order in response to a supplier's quotation does not establish a contract itself.
Main Page
Invitation for Bids – a solicitation of pricing information based upon a vendor’s evaluation of specifications or detailed work requirements to make an offer. Specifications or work efforts are not subject to negotiation or other post award revsions. A Bid can also be used under similar circumstances as a Quote but for a higher dollar threshold, when specified, by law or established policy. The solicitation will be publicized, in accordance with law or an established policy, with an adequate response time for bidders to respond by the submission date specified in the solicitation. An individual assessment of the work effort normally is utilized with an estimation of the supplies, materials, services or other costs will be required of the vendor/bidder to offer a price; usually in accordance with specification provided by a design professional. All vendors/bidders are expected to provide essentially the same product or service. The lowest Bid will be the best value.
|  |  |  | Main Page | SOW
Request for Proposal- a request for pricing information based upon a description of the purchaser’s particular requirements, typically in a scope of work [or scope of services]. The scope of work may contain contingent items [or iterations] that may or may not be ultimately performed. The solicitation is publicized, in accordance with law or an established policy, with an adequate response time provided for proposers to respond by the submission date specified in the solicitation. Proposers will be required to provide an individual assessment of the work effort that will be needed and an estimation of any supplies, materials, services or other costs that may be required by the proposer to offer a preliminary price. The issuer of the Proposal may permit offerors to propose different approaches or work products that ultimately meet the purchasers’ requirements. Some specifcation, work efforts,or task can be subject to negotiation or post award adjustnets. Proposals will also require qualitative evaluation of factors other than cost/price. Because qualitative considerations are usually involved in the selection, the lowest cost Proposal may not always be the best value.
Evaluation Factors

## Contracts
| Main Page | Planning
Contract Types |  | Below are the three different federal contract types to be utilized in procurement. They are mutually exclusive.
|  |  | Main Page | SOW
Firm fixed‐price. This contract type requires the delivery of product(s or service(s) at a specified price, fixed at the time of the contract award and not subject to any adjustment on the basis of the contractor’s cost experience in performing the contract. It is appropriate for use when fair and reasonable prices can be established at time of award, definite design or performance specifications are available, products are off‐the‐ shelf or modified commercial products or services with fixed performance requirements for which realistic prices can be offered, and any performance uncertainties can be identified, and reasonable cost estimated in advance. A purchase order issued by the [the purchasing/procurement authority] and which specifies the product, quantity of supplies or scope of work ordered, contains a determinable date by which delivery of the product, supplies
or performance of the work is required and contains a definitive price [lump sum or unit price with specified quanity] not subject to any contingencies may be considered a fixed price contract upon the acceptance and execution by [the purchasing/procurement authority]. Cost reasonableness is established by price competition with price/cost being the principal selection factor of the contractor. A fixed price contract places upon the contractor maximum risk and full responsibility for all costs and resulting profit or loss.
|  |  | Main Page | SOW
Cost‐reimbursement. Cost‐reimbursement types of contracts provide for payment of allowable incurred costs, to the extent prescribed in the contract's statement of work. These contracts establish an estimate of total cost for the purpose of obligating funds and establishing a ceiling that the contractor may not exceed (except at its own risk) without the approval of the [the purchasing/procurement authority]. Unlike a fixed price contract, the contractor may not necessarily receive the total amount of the cost ceiling because some items in the contract may not need to be delivered and /or factors other than price were considered in the selection. Cost reimbursement contracts are suitable for use primarily when uncertainties [in iterations or work efforts] involved in contract performance do not permit costs to be estimated with sufficient accuracy to use any type of fixed‐ price contract.
The contract's statement of work may state a definite goal or target and specify an end product(s) or accomplishment(s) (Completion form). The contract's statement of work normally requires the contractor to complete and deliver the specified end product(s) (e.g., a final report of research accomplishing the goal or target) within the estimated cost. Or in some circumstances the scope of work is stated in general terms and obligates the contractor to devote a specified level of effort for a stated time period (Term form). The contractor will provide a statement that the level of effort specified in the contract has been expended in performing the contract work. Because of the differences in obligation assumed by the contractor, the completion form is preferred over the term form whenever the work, or specific milestones for the work, can be defined well enough to permit development of estimates within which the contractor can be expected to complete the work.
Cost reimbursement contracts can contain all four types of prices. Payments can be made for complete units or distinct items of service or work products with an identifiable cost or price while other contract units or items remain undelivered. Cost reasonableness is established by cost analysis of the work products to be delivered. Contract performance and associated costs can be negotiated after contract award. Adjustments to costs for contract items publicized in the solicitation and contained in the statement of work are permitted. Because of the greater flexibility allowed in a Cost Reimbursement contract the UGLG and contractor share the risks for contract performance.
Main Page
Time and Materials contract. Under these contracts, the contractor’s services are pre-priced (usually, in terms of hours) in the contract, and the [the purchasing/procurement authority] orders services in unit amounts (e.g., hours) as needed until the funds in the contract are exhausted. Solicitations typically advertise for a scope of services allowable to be performed with no particular tasks to be performed or accomplisments specified. The [UGLG/Subrecipient] must have task order system in place for using this contract type. The [UGLG/Subrecipient ]'s may use this type of contract only after the [the purchasing/procurement authority] determines that no other contract type is suitable and if the contract includes a ceiling price that the contractor exceeds at its own risk. For reimbursement under Federal award, the [UGLG/Subrecipient NFE] must have obtained prior written approval from the Federal or pass through awarding agency. Cost reasonableness is established by detailed cost analysis. Time and materials contracts place most of the risk on the [UGLG/Subrecipient].
Purchases!B26

## Prices
| Main Page |  | Planning
Types of Prices |  | Below are the four different types federal prices that can be used in a contract. They are not mutually exclusive to the contract. Contracts may contain more than one type or price.
|  |  |  | Main Page | SOW
Lump Sum For definable work product or deliverable, whose value can be expressed as a single price inclusive of all production costs [labor, materials and purchased service costs, allowable overhead and profit]. The contractor will bear all the risks in producing the work product or deliverable at the agreed upon price. Because of the presumed certainty of contract task(s) or item(s) performance that qualifies a contract task or item as a Lump Sum price no adjustments to contract price are permitted. For fixed price contracts no change in quantities for any Lump Sum task(s) or item(s) would be permitted. Payment of total contract price will be made upon satisfactory performance, delivery and final acceptance of contract task(s) or deliverable item(s).
Main Page
Unit Price For definable work products or deliverables whose value can be expressed as a single price inclusive of all production costs [labor, materials and purchased service costs, allowable overhead and profit] for contract tasks or items and will be needed in two more iterations at the same agreed upon price. The contractor agrees to bear all the risks and cost variance in producing or performing the contract tasks or items at the agreed upon price per unit and for the quantities specified. For fixed price contracts, no change in quantities are permitted without an approved change order. If certain unit prices are contained in the initial contract, no deviations shall be allowed in computing negotiated change order costs. In cases where there is a discrepancy between the base bid total and the sum of the extended unit prices, the unit price bid shall govern.
|  |  |  | Main Page | SOW
Billable Hours For work efforts that are composed of predominately personnel compensation costs with a minimum of outside purchases of materials and services needed to produce a work product or provide a service; the contractor will be reimbursed for applied work efforts at the agreed upon billable hourly rate(s) inclusive of direct labor compensation, overhead, general and administrative expenses, and profit [fully burdened] by job title. Billable hours may be utilized for services or products that have a definitive accomplishment or product or may be used to reimburse work efforts for a scope of services with an accomplishment that cannot be estimated accurately.
|  |  |  | Main Page | SOW
Reimbursable Costs For work, efforts that require significant outside purchases of materials, services or from subcontractors in addition to the contractor's personnel compensation costs needed to produce a work product or service. The contractor's personnel compensation costs will be reimbursed for applied work efforts at the agreed upon hourly rate(s) by job title. The contractor's itemized outside purchases of materials and services will be reimbursed at invoice cost identifying items by quantities and/or cost per unit.

## Payments
| Main Page |  | Planning
Payment Types |  | Below are the three federal payment types to be used depending on the nature of the contract. They are mutually exclusive.
Main Page
Single Completion Payment Payment for completed item of work. Payment of the contract price is due upon completion and delivery of the [work] product and submission of the contractor's invoice. Payment is made upon delivery and acceptance of the purchased or contracted item.
|  |  |  | Main Page | SOW
Partial Completion Payment Payments for completed items of work. Partial payments are payments made, as authorized by the contract, upon delivery and acceptance of one or more complete units (or one or more distinct items of service or work products with a cost or price) in accordance with the contract specifications or statement of work, even though other quantities (or items) remain to be delivered. Can be used whenever the contract can be structured in terms of incremental stages or deliveries and there are appropriate acceptance criteria for the supplies, services or completed subsystems of a larger system. When the contract authorizes delivery or performance in increments, payment of a portion of the contract price may be made before the entire contract is completed.
Main Page
Progress Payment Progress payments are payments on its contracts based on a percentage or stage of completion of the work. Progress payments are for uncompleted work-in-progress. Progress payments are a type of contract financing, appropriate whenever the contractor will not be able to bill for the first-delivery of products, or other performance milestones, for a substantial time after work begins. The use of a retainage clause is authorized. Grantees may not use the percentage of completion method for non-construction contracts. For those contracts, progress [stage of completion] payments based on costs incurred must be used. The term "final payment" usually implies that both parties to the contract have fulfilled all of their responsibilities.

## Evaluation Factors
For the Competitive Proposal Method
Evaluation Factors | return Methods | return Solicitation
Evaluation Subjects: | to Determine: | Examples:
Qualifications | what the proposer peronnel are qualified to do- | Academic achievement, licenses, certifications and/or personnel experience of firm's personnel to be employed by this project
Experience | what has the proposer actually done- | firm's previous comparable projects by type, size and number,
Capabilities | what can the proposer do- | what and how many personnel and their qualification /specialties are available to perform the contract
Past Performance | how well has proposer done comparable work- | quantifiable measures proposer has performed previously
Approach Plan | that the objective, project description and scope of work all align;to project future performance | Proposers are asked for their recommendations on how to accomplish the "objective" implied in the program description

## Scoring
For the Competitive Proposal Method
| Scoring Methods |  |  | Methods
| Evaluation Subjects: | [5 empty] | Scoring Methods
[example] | Experience |  |  |  | Comparative Point Scale |  |  |  | Adjectival rating/subjective scoring
| Evaluation criteria: |  |  |  | Grouping Point Scale
[example] | number of projects conducted by proposers |  |  |  | Ordinal Ranking System
Weighted Point Scale
| Evaluation/Scoring basis: | [different scoring methods]
[6 empty] | Proposer A |  | Proposer B |  | Proposer C |  | points allocated
| Comparative Point Scale |  | projects conducted by each proposer |  |  | 12 |  | 8 |  | 10 |  | 30 | points
| The proposer with highest raw score sets the |  |  |  |  | [high raw score]
| scale with other proposers scaled accordingly. Can be used |  |  |  |  | 30 | pts. | 20 | pts. | 25 | pts. | points awarded
| in all scoring situations. Provides for a precise comparative | [6 empty] | 8/12 x 30 =20 |  | 10/12 x 30 =25
measurement of the evaluated items among the proposers.
| Grouping Point Scale |  |  |  |  | Groupings:
| Items to be scored are divided into |  |  |  |  | 10 or more projects 30 points |  |  |  | Proposers A [12], C [10]
| different increments and assigned points |  |  |  |  | 5 to 9 projects 20 points |  |  |  | Proposer B [8]
| according to their increments; used to |  |  |  |  | 4 or less 10 points
emphasize large differences in evaluated items
| Ordinal Ranking System |  |  |  |  | Proposer A |  | Proposer B |  | Proposer C
| Items are ranked according to their |  |  |  |  | First [12] |  | Third [8] |  | Second [10]
absolute values
| Weighted Point Scale |  |  |  |  | Proposer A |  | Proposer B |  | Proposer C |  | 30 | points
| Some components of evaluated items |  | total number of projects x 1 |  |  | 12 |  | 8 |  | 10
are more determinative for contractor
| selection and are scored with more points than others |  | number of similar projects |  |  | 4 |  | 2 |  | 6
|  |  |  | {weighted score x2} |  | {8} |  | {4} |  | {12}
|  |  | combined score |  |  | 20 |  | 12 |  | 22
[high raw score]
|  |  | points awarded |  |  | 27.2727 |  | 16.3636 |  | 30
| proposer data above not applicable |  | Evaluation Subjects: |  |  | Evaluation Subjects: |  |  |  |  | Evaluation Subjects:
|  |  | Approach Plan |  |  | Past Performance |  |  |  |  | Approach Plan
| Evaluation/Scoring basis: |  | Example 1 |  |  | Example 2 |  |  |  |  | Example 3
| Adjectival rating/subjective scoring |  | Adj Rating Descriptions/definitions |  |  | Adj Rating |  | Descriptions/definitions |  |  | Adj Rating | Description/definition
| Conducting evaluation on items based but upon a measurement of merit which are less precisely quantifiable but are distinguishable by a hiearchy of descriptive adjectives. Each adjectival rating must have a clear definition that differentiates from the other ratings in the heirarchy. |  | Outstanding | Proposer fully addresses all aspects of the criterion, convincingly demonstrates it will meet the governments performance requirements |  | Very Satisfactory |  | Performance met all contractual requirements and exceeded some to the Government's benefit. |  |  | Detailed | Proposer identifies all the necessary tasks need to accomplish the goals stated or implied in the project description and addresses all of the performance requirements with personnel/staffing
|  |  | Good | Proposer fully addresses all aspects of the criterion, convincingly demonstrates a liklihood of meeting the governments performance requirements |  | Satisfactory |  | Performance met contractual requirements. The contractual performance of the element or sub-element contains some minor problems for which corrective actions were taken |  |  | Sufficient | Proposer identifies most of the tasks need to accomplish the goals of the project description and addresses most of the performance requirements with personnel/staffing
|  |  | Adequate | Proposer addresses all aspects of the criterion, demonstrates an ability of meeting the governments performance requirements |  | Marginal |  | Performance did not meet some contractual requirements. The contractual performance of the element or sub-element being evaluated reflects a serious problem for which the contractor has not yet identified corrective actions |  |  | Acceptable | Proposer addresses the major performance requirements with personnel/staffing identified, rough time estimates for accomplishment of major tasks
|  |  | Poor | Proposer does not address all aspects of the criterion, nor is evidence presented of a liklihood of meeting the governments performance requirements |  | Unsatisfactory |  | Performance does not meet most contractual requirements and corrective actions are not likely in a timely manner. |  |  | Poor | Proposer addresses some of the major performance requirements, provides some projected timelines
|  |  | Unacceptable | Proposer does not address all aspects of the criterion, and evidence presented indicates a strong a liklihood offailure to meetthe governments performance requirements | [6 empty] | Unacceptable | Proposer does not address the major performance requirements,

## Eval Plan
For the Competitive Proposal Method |  | return Methods
EVALUATION PLAN COMPONENTS: | Explanation: | EXAMPLE
Evaluation Subject: | Identify the factor to be evaluated. | Proposer’s Capabilities: Measurement: Size of Staff by skill level
Evaluation criteria: | Identify what items will be evaluated. | Proposer’s personnel by job specialty and number
Rating Factor Rationale: | Explain the reason the factor is relevant to this contractor selection. | Assumes larger workforce available will be more responsive and timely in contract performance
Submission requirements: | Identify the items proposers must submit for factor evaluation. | Proposers will submit the job titles required for the project and the number of those employed in those job titles
Evaluation/Scoring basis: | Explain how the items will be evaluated and scored. | Proposers will be scored by the number job positions and number of incumbents by job title and be awarded scores on a comparative point basis
|  |  |  | Proposer A |  | Proposer B | Proposer C
|  |  |  | Projects by Program Year |  | Projects by Program Year | Projects by Program Year
|  |  | FY | 2019 | 2 | 1 | 2
|  |  | FY | 2018 | 4 | 2 | 1
|  |  | FY | 2017 | 1 | 1 | 3
|  |  | FY | 2016 | 3 | 2 | 2
|  |  | FY | 2015 | 2 | 2 | 2
[5 empty] | 12 | 8 | 10
Proposers will identify by job title the firm's personnel to be asigned to the project

## Elements
Elements of a Procurement Procedure |  |  |  | return Methods
The procurement procedure that a recipient develops for the different procurement methods must address each of the following elements.
Cost/price thresholds procurement for Method
Identify the applicable Federal and State [and local] price/cost thresholds, both maximum and minimum, that govern the use of the procurement method.
return Purchase Types
Price/Cost information and category of purchase for procurement Method
Identify the categor(ies) of purchase(s) and how price/cost information will be obtained for the procurement method.
Requirements for use of the procurement Method
Specify the general and/or any particular requirements and/or applicable restrictions for using the procurement method.
return Solicitation Types
Solicitation requirements to follow for procurement Method
Describe any Federal and State mandated or locally developed requirements for solicitation and additional procedures that can achieve effective competition results.
Cost reasonableness procedures for procurement Method
Describe how price analysis/comparison or cost analysis will be applied to the procurement.
return Selection
Selection and contract award procedures for procurement Method.
Identify the basis of contractor selection; lowest price, qualifications or best value [combination] and how it will be determined; publized evaluation factors and their weights and details of the price offer.
return Contract | return Price |  | return Payment
Contract type, Price type(s) and Payment type for the procurement Method
Describe the federal contract type, the price type(s) and terms of payment for the procurement.
Procurement Records for procurement Method
List the applicable records associated with the procurement method; UGLG authorization for purchase/procurement; copies of solictations/advertisements; copies of offers/bids/proposals, minutes of pre-bid or pre-proposal conferences; copies of evaluations, minutes of bid openings, scoring of proposals; minutes of contact negotitions, pre-award conferences; copies of contracts, copies of invoices and payments; copies of inspections or other performance monitoring; copies of completion or termination notifications.

## Contracted Services
Main Page
Type of Purchase
Scope of Work |  |  |  | Vendors with specific qualifications, capabilities and/or licenses that provide particular services needed to perform the SOW
Contracted Services Procurement |  |  |  | Costs of professional and consultant services rendered by persons who are members of a particular profession or possess a special skill and who are not officers or employees of the recipient or subrecipient. Professional Services means non-construction services that require an advanced degree or professional licensing, including, but not limited to, contracts for legal services, financial consulting, accounting services, environmental assessment, architectural services, and civil engineering services.
COMPONENTS |  | TYPES
Purchase Types |  | Scope of Work (SOW) Purchase
Methods of Procurement |  | Competitive Proposals
| alternative |  | Micro-Purchase | for single product provided by a professional provider less than $10,000
| alternative |  | Simplified Acquisition | for products that not require detailed specifications in total under $250,000
Contractor Selection |  | Combination
| alternative |  | Qualifications | for A/E services only
Solicitation Types. |  | Request fo Proposal
| alternative |  | Quote | for single product provided by a professional provider
Contract Types |  | Cost‐reimbursement
| alternative |  | Firm fixed‐price | for single product provided by a professional provider
Types of Prices |  | Billable Hours
| alternative |  | Reimbursable Costs | includes significant costs beyond personnel compensation
| alternative |  | Lump sum | for individual products that can be delivered with all production
costs contained in a single price for each product
| alternative |  | Unit Price | for muliple iterations of the same product
Payment Types |  | Partial Completion Payment
| alternative |  | Single Completion Payment | for single product provided by a professional provider

## Public Works
Main Page
Type of Purchase
Public Works Construction |  |  | Public work means the erection, construction, alteration, improvement, or repair of any public facility or immovable property owned, used, or leased by a public entity.
Components |  | TYPES
Purchase Types |  | Design Specifications Purchase.
Methods of Procurement |  | Sealed [Advertised] Bid
Contractor Selection |  | Price
Solicitation Types. |  | Invitation for Bids
Contract Types |  | Firm fixed‐price
Types of Prices |  | Lump Sum Price
| alternative |  | Unit Price
Payment Types |  | Progress Payment

## Eq Sup Mtr
Main Page
Type of Purchase:
Specified Product, Brand Name or Equal Specifications Purchase. |  |  |  | Supplies tangible personal property other than equipment with a per-item acquisition cost of $5000 or less.
Equipment, Supplies, Materials
Equipment tangible, non-expendable, personal property having a useful life of more than one year and an acquisition cost of $5,000 or more per unit.
COMPONENTS |  | TYPES
Purchase Types |  | Specified Product, Brand Name or Equal Specifications Purchase.
Methods of Procurement |  | Simplified Acquisition
| alternative |  | Sealed [Advertised] Bid | for supplies or materials over $60,000
| alternative |  | Micro-Purchase | for supplies or materials under $10,000
Contractor Selection |  | Price
| alternative |  | Combination | certain technical specifications of equipment purchases
Solicitation Types. |  | Quote
| alternative |  | Invitation for Bids | for supplies or materials over $60,000
Contract Types |  | Firm fixed‐price
Types of Prices |  | Lump Sum Price
| alternative |  | Unit Price | if the purchase is for multiple iterations
Payment Types |  | Single Completion Payment